## PMR 2022
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | Department of Tourism - Region III Procurement Monitoring Report as of January 6, 2023
Code (UACS/PAP) | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [9 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion |  | Total | MOOE | CO | Total | MOOE | CO
COMPLETED PROCUREMENT ACTIVITIES
| Photocopying Services for DOT Region III | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | February 10, 2022 | February 20, 2022 | February 22, 2022 | March-December 2022 |  | 77000 |  |  | 58800
| DOT Region III Office Lease | [19 empty] | DOT Region III | Negotiated Procurement - Real Property | [6 empty] | February 4, 2022 | February 16, 2022 | February 17, 2022 | March-December 2022 |  | 2459160 |  |  | 1296900
| Hiring of a Training Service Provider for Community-based Tourism Kulinarya Workshop in Baler, Aurora | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | February 16, 2022 | February 17, 2022 | February 18, 2022 | February 22-24, 2022 |  | 350000 |  |  | 345000
| Hiring of a Training Service Provider for the Seminar on Filipino Brand of Service Excellence with Tour Guiding Techniques and Commentary Development for Accommodation Sector | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | February 17,2022 | February 21, 2022 | February 21, 2022 | February 28 to March 3, 2022 |  | 201900 |  |  | 192000
| Hiring of a Training Service Provider for the Seminar on Filipino Brand of Service Excellence for Farm Tourism Owners/Managers and Staff in the Province of Aurora | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | February 17,2022 | February 21, 2022 | February 23, 2022 | February 23-24, 2022 |  | 102700 |  |  | 100200
| Procurement of Services of an Events Management Company for the Central Luzon Tourism Investment Summit and Business Exchange (CLTISBEX) | [19 empty] | DOT Region III | Competitive Bidding | February 7, 2022 | February 14-March 7, 2022 | February 23, 2022 | March 7 and March 9, 2022 | March 11, 2022 | March 22, 2022 | April 1, 2022 | April 10, 2022 | April 12, 2022 | May 4-5, 2022 |  | 4375000 |  |  | 3297000 |  |  | 3
| Hiring of a Service Provider/Tour Operator for the conduct of Bohol/Cebu-Clark Inbound Tourism Exchange (Clark-Silangin, Zambales Island Hopping-Subic Bay Sunset Cruise) | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | March 8, 2022 | March 9, 2022 | March 10, 2022 | April 4-7, 2022 |  | 998768 |  |  | 983768
| Transportation Hire (Van Rental) for the DOT Region III Accreditation Officers | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | March 15, 2022 | March 16, 2022 | March 17, 2022 | March 21 to April 1, 2022 |  | 94000 |  |  | 78000
| Catering Services for the Lunch of VIPs on the 80th Commemoration of Araw ng Kagitingan | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | March 23, 2022 | March 23, 2022 | March 24, 2022 | April 9, 2022 |  | 70000 |  |  | 70000
| Procurement of Services of App Developers for the Central Luzon Travel Portal and Mobile Application | [19 empty] | DOT Region III | Competitive Bidding | March 30, 2022 | April 14 to May 10, 2022 | April 27, 2022 | May 10, 2022 | May 18, 2022 | May 18, 2022 | May 23, 2022 | June 2, 2022 | June 7, 2022 | June-December 2022 |  | 3000000 |  |  | 2217777 |  |  | 3
| Hiring of an Accredited Tour Operator for the 4 Day/3 Nights Clark-Busuanga Travel Exchange | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | May 4, 2022 | May 5, 2022 | May 10, 2022 | May 24-27, 2022 |  | 997000 |  |  | 982000
| Procurement of Accommodation, Meals, and Venue for the Eco-Tour Guides Training in Arayat, Pampanga | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | May 16, 2022 | May 16, 2022 | May 17, 2022 | May 18-24, 2022 |  | 182000 |  |  | 182000
| Hiring of a Training Service Provider/Tour Operator for the Eco-Tour Guides Training in the Municipality of Casiguran, Aurora | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | May 17, 2022 | May 18, 2022 | May 19, 2022 | May 23-30, 2022 |  | 500000 |  |  | 490000
| Meals and Accommodation for the Eco-Tour Guides Training in Arayat, Pampanga | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | May 16, 2022 | May 16, 2022 | May 17, 2022 | May 18-24, 2022 |  | 182000 |  |  | 182000
| Hiring of a Training Service Provider/Tour Operator for the Eco-Tour Guides Training for the Indigenous People of Palayan City, Nueva Ecija | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | May 16, 2022 | May 16, 2022 | May 17, 2022 | June 17-23, 2022 |  | 375000 |  |  | 373000
| Hiring of a Tour Operator/Grounc Handler for the Kain Na! Food and Travel Festival 2022 | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | May 30, 2022 | May 31, 2022 | June 1, 2022 | June 7-9, 2022 |  | 177000 |  |  | 175001
| Accommodation, Meals, and Venue for the Training on Fun Farms Tour Guiding with Filipino Brand of Service Excellence | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | May 31, 2022 | June 1, 2022 | June 3, 2022 | June 6-9, 2022 |  | 84000 |  |  | 82230
| Hiring of a Tour Operator/Ground Handler for the Launching of Travel, Breathe, and Dive | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | May 31, 2022 | June 3, 2022 | June 10, 2022 | June 21-24, 2022 |  | 986150 |  |  | 975150
| Hiring of a Training Service Provider/Consultancy Services for Community-Based Tourism Kulinarya Workshop in Palauig, Zambales | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | June 13, 2022 | June 16, 2022 | June 17, 2022 | June 22-25, 2022 |  | 350000 |  |  | 345000
| Procurement of Meals for the Eco-Tour Guides Training in Porac, Pampanga | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | June 13, 2022 | June 17, 2022 | June 20, 2022 | June 24-30, 2022 |  | 98000 |  |  | 98000
| Services of a Tourist Transport/Tour Operator during the Soul Circuit Revalidation and Investment Tour | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | June 15, 2022 | June 16, 2022 | June 17, 2022 | June 20-21, 2022 |  | 80000 |  |  | 73000
| Hiring of a Training Service Provider/Tour Operator for World War II Community Guides Training (Second Posting) | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | June 27, 2022 | June 28, 2022 | June 29, 2022 | July 7-13, 2022 |  | 400100 |  |  | 389400
| Meals for the Filipino Brand of Service Excellence with Tour Guiding Techniques and Commentary Development in the Provicne of Bataan | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | June 29, 2022 | June 30, 2022 | July 1, 2022 | July 5-8, 2022 |  | 70000 |  |  | 68600
| Meals for the Filipino Brand of Service Excellence with Tour Guiding Techniques and Commentary Development in the Province of Bataan | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | June 29, 2022 | June 30, 2022 | July 1, 2022 | July 5-8, 2022 |  | 70000 |  |  | 68600
| Hiring of a Training Service Provider/Tourism Consultancy Services for the Eco-Tour Guides Training in Capas, Tarlac | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | July 27, 2022 | July 28, 2022 | July 29, 2022 | August 5-11, 2022 |  | 430000 |  |  | 409900
| Accommodation, Meals and Venue for the Training on Filipino Brand of Service Excellence with Basic Tour Guiding and Commentary Development in the Province of Bulacan | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | July 27, 2022 | July 28, 2022 | July 29, 2022 | August 1-4, 2022 |  | 108000 |  |  | 107932
| Hiring of a Tour Operator/Ground Handler for the Participants of the DOT Region III Office to the Philippine Dive Expo (PhiDEX) 2022 | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | August 2, 2022 | August 3, 2022 | August 4, 2022 | August 18-22, 2022 |  | 250000 |  |  | 241112
| Procurement of Accommodation, Meals, and Venue for the Cultural Community Guides Training in SBFZ | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | August 2, 2022 | August 3, 2022 | August 4, 2022 | August 6-12, 2022 |  | 222250 |  |  | 221900
| Hiring of a Training Service Provider for the Eco-Tour Guides Training in the Province of Bulacan | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | August 22, 2022 | August 23, 2022 | August 24, 2022 | August 25-September 2, 2022 |  | 430000 |  |  | 425000
| Hiring of a Tour Operator/Ground Handler for the Accreditaion Caravan in the provinces of Aurora, Bulacan, Bataan, and Zambales (Second Posting) | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | September 1, 2022 | September 2, 2022 | September 5, 2022 | September 7-October 28, 2022 |  | 225000 |  |  | 224500
| Hiring of a Tour Operator/Ground Handler for the Development and Validation of the WWII Historical Tour (Second Posting) | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | September 5, 2022 | September 13, 2022 | September 20, 2022 | September to October 2022 |  | 992060 |  |  | 980949
| Meals and Venue for the Filipino Brand of Service Excellence for Accredited Tourist Drivers in Central Luzon | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | September 7, 2022 | September 8, 2022 | September 9, 2022 | September 26-27, 2023 |  | 63000 |  |  | 63000
| Hiring of a Tour Operator/Ground Handler for the Launching of Surf and Glamp Adventure - Zambales (Third Posting) | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | September 14, 2022 | September 19, 2022 | September 20, 2022 | September-October 2022 |  | 600000 |  |  | 599000
| Meals and Venue for the Eco-Tour Guides Training in Lubao, Pampanga | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | September 13, 2022 | September 14, 2022 | September 15, 2022 | September 17-23, 2022 |  | 120050 |  |  | 120050
| Meals and Venue for the Cultural Community Guides Training in the Province of Bataan | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | September 14, 2022 | September 14, 2022 | September 16, 2022 | September 17-23, 2022 |  | 147000 |  |  | 140000
| Services of a Booth Contractor for the Design/Layout, Set-Up, and Dismantling of the DOT Region III's booth at the Philippine Travel Mart (PTM) | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | September 19, 2022 | September 20, 2022 | September 21, 2022 | September 29-October 3, 2022 |  | 180000 |  |  | 177366.56
| Catering of Meals for the Business Networking with FPACC and CL Stakeholders (Second Posting) | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | October 11, 2022 | October 12, 2022 | October 14, 2022 | October 17, 2022 |  | 102000 |  |  | 60000
| Hiring of MICE Organizer/Ground Handler for the DOT Central Luzon Tourism Recognition Night 2022 | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | November 7, 2022 | November 8, 2022 | November 9, 2022 | December 5, 2022 |  | 355000 |  |  | 355000
| Venue for the conduct of the 1st North Luzon Travel Fair in Clark Freeport Zone | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | October 25, 2022 | October 28, 2022 | November 16, 2022 | November 17-21, 2022 |  | 950000 |  |  | 936179.94
| Services of a Booth Contract for the Design/Layout, Set-Up, and Dismantling of the DOT Region III's Pavilion at the 1st North Luzon Travel Fair | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | November 3, 2022 | November 4, 2022 | November 16, 2022 | November 17-21, 2022 |  | 450000 |  |  | 438000
| Hiring of a Tour Operator or Ground Handler for the conduct of the Caticlan-Clark Inbound Tourism Exchange | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | November 3, 2022 | November 10, 2022 | November 11, 2022 | November 18-21, 2022 |  | 995200 |  |  | 993900
| Tour Operator or Ground Handler for the conduct of the Inter-Regional Exchange with Davao Stakeholders | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | November 3, 2022 | November 8, 2022 | November 9, 2022 | November 18-21, 2022 |  | 158500 |  |  | 151720
| Hiring of a Tour Operator / Ground Handler for the MIMAROPA - Clark - MIMAROPA Tourism Exchange | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | November 3, 2022 | November 11, 2022 | November 14, 2022 | November 18-21, 2022 |  | 870200 |  |  | 812780
| Hiring of a Tour Operator / Ground Handler for the Kain Na! Food and Travel Festival 2022 | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | November 4, 2022 | November 7, 2022 | November 8, 2022 | November 10-14, 2022 |  | 368500 |  |  | 358000
| Accommodation for the Exhibitors/MSMEs to participate in the Trade Fair in conjuction with the National Farm Tourism Summit and Trade Fair | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | November 7, 2022 | November 18, 2022 | November 21, 2022 | November 30-December 5, 2022 |  | 210000 |  |  | 180000
| Accommodation for the Attendees of the National Farm Tourism Summit | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | November 7, 2022 | November 18, 2022 | November 21, 2022 | November 30-December 5, 2022 |  | 445000 |  |  | 444520
| Printing of DOT R3 Tourism Brochures | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | November 8, 2022 | November 9, 2022 | November 10, 2022 |  |  | 255000 |  |  | 178200
| Supply and Delivery of Three (3) Motor Vehicles | [19 empty] | DOT Region III | National Competitive Bidding | October 28, 2022 | November 3, 2022 | November 11, 2022 | November 23, 2022 | November 24, 2022 | November 27, 2023 | November 28, 2022 | December 14, 2022 | December 16, 2022 | December 27, 2022 |  | 4565000 |  |  | 2892620
| Hiring of a Tour Operator/Travel and Tour Agency/Travel Agency for the Event Venue, Meals, Technical Tour, and Transportation for the National Farm Tourism Summit and Trade Fair (Second Posting) | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | November 11, 2022 | November 18, 2022 | November 21, 2022 | November 30-December 5, 2022 |  | 973800 |  |  | 973800
| Supply and Delivery of One (1) Motor Vehicle | [19 empty] | DOT Region III | Small Value Procurement |  | November 16, 2022 | November 28, 2022 | November 29, 2022 | December 1, 2022 | December 2, 2023 | December 6, 2022 | December 21, 2022 | December 22, 2022 | December 27, 2022 |  | 1800000 |  |  | 1755500
| Consultancy Services for the Dossier of UNESCO ICH Pagduduman Nomination of Pampanga (Second Posting) | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | November 16, 2022 | November 29, 2022 | December 1, 2022 | December 2022-February 2023 |  | 500000 |  |  | 500000
| Services of an Events Management Company for the National Farm Tourism Summit and Trade Fair 2022 (Third Posting) | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | November 21, 2022 | November 22, 2022 | November 23, 2022 | November 30-December 5, 2022 |  | 823000 |  |  | 822453
| Supply and Delivery of One (1) Motor Vehicle (Reposting) | [19 empty] | DOT Region III | Small Value Procurement |  | November 25, 2022 | December 5, 2022 | December 19, 2022 | December 21, 2022 | December 22, 2022 | December 23, 2022 | December 24, 2022 | December 29, 2022 |  |  | 1600000 |  |  | 1464240
| Hiring of a Training Service Provider for the Eco-Tour Guides Training in Carranglan, Nueva Ecija (4th Posting) | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | December 6, 2022 | December 7, 2022 | December 9, 2022 | December 11-19, 2022 |  | 430000 |  |  | 429000
| Renovation of the DOT Region III Office | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | December 9, 2022 | December 12, 2022 | December 13, 2022 | December 2022-February 2023 |  | 840000 |  |  | 830000
| Security Services for the DOT Region III Office | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | December 12, 2022 | December 21, 2022 | December 29, 2022 | January to December 2023 |  | 720000 |  |  | 663120
| Hiring of a Tour Operator/Ground Handler for the Year-End Assessment, Planning Session, and Filipino Brand of Service Excellence Training | [19 empty] | DOT Region III | Small Value Procurement | [6 empty] | December 23, 2022 | December 24, 2022 | December 26, 2022 | December 27-29, 2022 |  | 308100 |  |  | 298888
0N-GOING PROCUREMENT ACTIVITIES
Total Alloted Budget of On-going Procurement Activities | [33 empty] | 37766438 |  |  | 32372056.5
[21 empty] | Prepared by: | [7 empty] | Recommended for Approval by: | [7 empty] | APPROVED:
| REALYN C. MANALO / JEAN PIAGET C. MANABAT | [25 empty] | ALLEN S. GONZALES | [9 empty] | AVON D. TIMBOL
[21 empty] | BAC Secretariat | [5 empty] | BAC Chairperson | [9 empty] | Head of the Procuring Entity